## Sheet1
Tasks | Time Expenses | Description | Done | Responsible | Due Date
Project preperation | 2 h | install Angualr, NodeJS and Ionic | Yes | Simon Blaha | 24.01.2019
Project preperation | 2 h | install Angualr, NodeJS and Ionic | Yes | Tarik Hosic | 24.01.2019
Project preperation | 2 h | install Angualr, NodeJS and Ionic | Yes | Johann Haag | 24.01.2019
Server | 3 - 5 h | Installation and commissioning of a fake rest server | No | Johann Haag | 24.01.2019
Server | 15-21 h | Coding of a rest server | No | Simon Blaha | 14.02.2019
Log In | 5-8 h | Screen and functionality | No | Tarik Hosic, Johann Haag | 14.02.2019
Basic functions | 10-15 h | Adding, removing and configurating of appointments | No | Johann Haag | 14.02.2019
Display | 8-15 h | Display of the basic functions | No | Tarik Hosic | 14.02.2019